ITECH Curriculum Development Process Checklist

Acronym Legend:

CPM = Country Project Manager		LCD = Lead Curriculum Developer

MRT = Manager, Resource Team		CER = Content Expert (Outside) Reviewer

CTL = Curriculum Team Lead		M&E = M & E Team Member

CD = Curriculum Developer			CPE = Copy Editor

CE = Content Expert				AC = Administrative Coordinator

MD = Media Developer

I. Request for Training Curricula

| What | Who |
| --- | --- |
| Define Request | CPM → MRT & CTL |
| Topic (OI Treatment / ARV / Home Care / Counseling & Testing / Rapid Testing) |  |
| Audience |  |
| Type of Materials Needed (Facilitator Guide / Participant Manual / PowerPoint / Brochures) |  |
| Approximate Timeline (Especially if Training Date is Established) |  |
| Content experts (Who is slated to contribute) |  |
| Learning Goals (knowledge, skill development, clinical skills, TOT, etc.) |  |
| Potential Media Needs |  |
| Budget |  |
| Language Issues (English fluency, translation needed, etc.) |  |
| Cultural Issues |  |

II. Pre-Planning

| Define Target Audience | CPM →CTL |
| --- | --- |
| Their Profession: |  |
| Approx Years in Profession: |  |
| New to HIV: |  |
| Specific training needs: |  |
| Define Client’s Training Material Format Expectations | CPM →CTL |
| Overhead (vertical / Horizontal) |  |
| PowerPoint Presentation (vertical / Horizontal / Animation) |  |
| Photos (black and white / color) |  |
| Written Educational Materials (trainers’ manual / participants’ manual / handouts / work aids / brochures / posters) |  |
| Media (trigger tapes / audio / website / videoconferencing) |  |
| Language |  |
| Define Procedures to Interface with In-Country Partners | CPM →CTL |
| Printing Materials |  |
| Address for Sending Materials |  |
| Identify Country Partners (contact information; identify process of communication) |  |
| Country Review Process and Input (Identify Country Reviewers; Contact Information; Define Review Process) |  |
| Identify Appropriate Logos |  |
| Establish Development Team | CTL |
| CTL (write contract, clarify goals, tasks, responsibilities, etc.) |  |
| LCD (may be same as CTL; contact info; schedule of availability) |  |
| CD (contact info; schedule of availability) |  |
| CE (contact info; schedule of availability) |  |
| MD (contact info; schedule of availability) |  |
| M&E (schedule of availability) |  |
| CER (only for second and final versions; contact info; schedule of availability) |  |
| CPE (only for final version; contact info; schedule of availability) |  |

III. Manual Preparation for Pilot

| Develop Rough Outline | CE →CD+CPM |
| --- | --- |
| Identify Primary Topics and Subtopics |  |
| Establish Logical Order and Approximate Length of Time |  |
| Review Outline to Assure Client’s Training Needs are Accurately Reflected | CPM |
| Prepare CE for Content Dev (Verify PP Template / Provide CE with PowerPoint Template ) | CD →CE |
| Create Content for Manual (Fill-in Content / Create PowerPoint Slides) | CE →CD |
| Manual Set-up Work | CD |
| Set-Up Word Document Manual Template |  |
| Set-up Document “Shells” for Content |  |
| Determine Use of Educational Media (contact media producer / obtain timeline) | CTL + MD |
| Determine M & E Approaches | CTL+LCD+M&E |

IV. Pilot Development

| Provide Content (content for all modules, case studies, discussion points, etc.) | CE →CD |
| --- | --- |
| Provide Clinical Photos (CD can also search for extra photos online) | CE →CD |
| Create Facilitator’s Guide | CD |
| Develop Exercises, case study, role plays, etc and instructions/answers for them |  |
| Create Worksheets for activities and educational media |  |
| Provide “discussion points” and guide for educational media |  |
| Create Drafts of Sections One and Two (use Previous I-TECH manuals for template) |  |
| Create complete draft of each module/session/unit in Section 3 |  |
| Create Participant’s Handbook (usually from Facilitator’s Guide) | CD |
| Develop Educational Media | MD |
| Develop Evaluation Tools (pre-post assessment, course evaluation, daily evaluation, etc.) | CE + CD + M&E |

V. Pilot Review

| 1. Content Expert Review (Reviews PowerPoint and Exercise Worksheets for Content) | CE |
| --- | --- |
| 2. Curriculum Developer Review (applies changes from CE/ readies manual for LCD review) | CD |
| 3. Overall Manual Review (Content, Editing, PowerPoint Agreement / Completeness / Professionalism) | LCD |

VI. Pilot Version

| Create PDF (If necessary; Resource Team can assist) & CD-ROM | CD or LCD |
| --- | --- |
| Send to Country | LCD |
| Administer Pilot | CPM |
| Observe First Pilot and Document Suggested Revisions | CE / CPM / M&E |

VII. Pilot Revision

| Review of Potential Pilot Changes (content, structure, activity, media, evaluation/assessment, etc. changes) | CE + CD+ CPM + LCD + M&E |
| --- | --- |
| Establish Pilot Revision Process | CE+CD |
| Team Clarification and Roles and Responsibilities | CE+CD |
| Timeline | CE+CD |
| Apply Revisions | CE+CD |
| Conduct Pilot Revision Review |  |
| 1. Content Expert Review (Reviews PowerPoint and Exercise Worksheets for Content) | CE |
| 2. Curriculum Developer Review (applies changes from CE/ readies manual for LCD review) | CD |
| 3. Overall Review (Content, Editing, PowerPoint Agreement /Completeness/Professionalism) | LCD |

VIII. Second Version

| Create PDF (If necessary; Resource Team can assist) | CD |
| --- | --- |
| Distribute to Country | CD |
| Deliver Second Version Training | CPM |
| Observe Second Version Training Delivery and Document Suggested Revisions | CE / CPM / M&E |

IX. Second Revision and Review

| Review of Potential Changes (content, structure, activity, media, evaluation/assessment, etc. changes) | CE + CD+ CPM + LCD + M&E |
| --- | --- |
| Establish Second Revision Process | CE+CD |
| Team Clarification and Roles and Responsibilities | CE+CD |
| Timeline | CE+CD |
| Conduct Second Revision | CE+CD |
| Conduct Second Revision Review |  |
| 1. Content Expert Review (Reviews PowerPoint and Exercise Worksheets for Content) | CE |
| 2. Curriculum Developer Review (applies changes from CE/ readies manual for LCD review) | CD |
| 3. Overall Review (Content, Editing, PowerPoint Agreement /Completeness/Professionalism) | LCD |

X. Final Copy

| Copy Edit (Must have at least one revision prior, could have more; LCD or CTL arranges) | CPE |
| --- | --- |
| Final Logo Decisions and Partner Permissions | CPM |
| Final Content Expert (Outside) Review | CER |
| Final Curriculum Review | CTL |
| Final Media Review | MD |
| Produce Bound Copies (in country, outside organizations, I-TECH library) | LCD / CTL |
| Produce Media Copies | MD |

XI. Dissemination

| Distribution of Final Copies (in country, outside organizations, I-TECH library) | CPM + CTL |
| --- | --- |
| Manage Requests for Copies of Educational Media and Manuals | CTL + AC |