# Training Material Production Workplan: 
From Concept to Product

# Overview

When good content is matched with an appropriate design, even the most complex documents become appealing, credible, and easy to read. In fact, studies have shown that using the right design elements can have a positive impact on how well readers understand the material.

We have designed this planning tool to guide staff through the process of developing training material. It provides descriptions of each step in the process as well as guidelines for setting our production timeline. It assumes you will be creating a document of average length (e.g., 4 to 100 pages). The process and timeline may differ for very short or very long documents.

Once you have developed a document’s basic content, the publication development process generally proceeds in two stages:

- The draft stage—all participants have input on all aspects of the project: Planning, Content Development, Draft Layout and a Preliminary Review

- The final stage—the final layout incorporates the final text and images; the materials are sent to the printer: Final Layout, Final Review, Printing, and After Printing

Review all of the steps in this document before beginning the process. Some stages—such as content development and initial design—may overlap, so take all steps into consideration. Careful planning and follow-up help ensure that the process goes as well as possible.

# Project Details

Start the production process by providing the basic project information.

Project title:

Project lead (primary contact and decision maker):

Graphics lead (primary graphics contact):

Date: _________________________________	   Project Code:

# Publications Development Process

# Draft Stage

| Planning |
| --- |
| Step 1 | Description |
| Planning meeting | It’s important to start this process out on the right foot. Begin by having the project lead arrange a meeting with key project, editorial, and graphics staff to discuss: |
|  | goals and priorities audience | dissemination plans translation plans | timeline budget/printing options |
|  | The project team should bring sample designs if they have a particular style in mind. |

| Content Development |
| --- |
| Step 2 | Description | Est. Timeline | Date Due | Staff Lead |
| Draft text | Author(s) plans and prepares draft text. If multiple authors provide material, the project lead must compile text. | Varies |  |  |
| Word processing | Support person cleans up text per accepted style manual. | Varies |  |  |
| Editing | An editor usually ensures that the document is well organized, clear, and cohesive, and that it fulfills readers’ needs. This fresh set of eyes is very helpful to those involved in creating the document. Editor may provide suggestions that the author will need to address, so allow sufficient time. | 1 to 4 pg/hr |  |  |
| Reviewer input | Project lead obtains programmatic input from relevant reviewers, internally and/or externally. | Varies |  |  |
|  | Medical reviewer ensures that technical content is accurate and up-to-date. |  |  |  |
|  | Cultural reviewer(s) ensures that the content (in particular the examples/role plays/case studies) represents, and is acceptable to, the population. |  |  |  |
| Incorporate reviewer input | Project lead incorporates reviewer input. If input is substantial, project lead may want to work with the editor to incorporate changes. | Varies |  |  |
| Proofreading | Prior to finalizing text, project lead arranges for proofing by a designated proofreader. Using someone unfamiliar with the document is usually best. | 5 pg/hr |  |  |

| Draft Layout and Preliminary Review |
| --- |
| Step 3 | Description | Est. Timeline | Date Due | Staff Lead |
| Preliminary design concepts | Graphics lead drafts one or more designs for the team to review. The project lead provides graphics staff with the draft text and any images or supporting graphics. | 5 days |  |  |
| Brief meeting | Graphics and project leads review the preliminary designs and discuss refinements if needed. The writer is often at these meetings. Everyone is clear on the time the printer needs to complete the project. | 3/4 to 1-hour meeting |  |  |
| Photo selection, illustration | If needed, the graphics team searches for new photos or creates illustrations. Project lead must obtain permission for using proprietary images. | Varies |  |  |
| Initial layout | Graphics team flows in the initial text and places the graphic elements. | 3 pg/hr |  |  |
| Team review of designs and initial layout | The project team may review and comment on all design aspects and consider how the text reads in layout form. We recommend having all relevant team members and reviewers provide input at this time. | 3 days |  |  |
| Discussion | Project lead and graphics staff should meet to discuss refinements. | 1-hour meeting |  |  |
| Revisions | If text changes are needed, project lead consults with graphics to determine how changes should be incorporated (for example, into a new Word file vs. existing design files). If significant layout changes are needed, team must return to the “Preliminary Design Concepts” stage. | --- |  |  |
| Finalize specs | Project lead and graphics staff finalize printing specifications. This is the “last call” for decisions about the size, number of colors, binding, etc. | --- |  |  |

# Final Stage

| Final Layout and Final Review |
| --- |
| Step 1 | Description | Est. Timeline | Date Due | Staff Lead |
| Text finalized | Project lead finalizes content. He or she has incorporated into the “Final”: All team input. All sections and images. A designated proofreader has proofread the Word file. | Varies |  |  |
| Design refinement and layout of final text | The project lead gives final text to the graphics lead in electronic form. This also is the “last call” for images. | 1 to 5 pg/hr |  |  |
| Final team review | Project lead (and relevant staff if needed) confirms that the final version is acceptable. Only typos can be corrected at this time. | Varies. Average: 3 days |  |  |
| Final revisions | Project lead goes through final revisions. Only minor changes, if any, can be made at this point. Significant revisions will result in serious delays. | 1 day |  |  |

| Printing |
| --- |
| Step 2 | Description | Est. Timeline | Date Due | Staff Lead |
| Files preparation for printer | Graphics staff packages files for printer (after adjusting resolution of images, performing final color corrections, etc.). | 1 day |  |  |
| Printer proofs/ bluelines | Graphics staff and project lead review proofs/bluelines from printer. | The printing process takes approx. 10 working days. Printer establishes schedule. |  |
| Press check | Press check by graphics staff or project lead is recommended for most jobs. |  |  |

| After Printing |
| --- |
| Step 3 | Description | Est. Timeline | Date Due | Staff Lead |
| Boxes arrive from printer | Project lead ensures that a plan is in place for moving boxes to an acceptable storage place; or has a plan for distributing the materials. |  |  |  |
| Incorporate changes into Word file | If the original Word file might be used for other purposes, the project lead ensures the incorporation of changes made during final layout and blueline review. |  |  |
| Celebration! | Be sure to take time to celebrate your accomplishment! |  |  |

Adapted from material developed by Michele Burns, Program for Appropriate Technology and Health (PATH), http://www.path.org/